## WBS with Gantt Chart BLANK
WORK BREAKDOWN STRUCTURE WITH GANTT CHART
PROJECT TITLE |  | GANTT |  |  |  |  | COMPANY NAME | [8 empty] | SeniorAdopt
PROJECT MANAGER |  | Group 10 |  |  |  |  | DATE | [8 empty] | 2021-10-20
[7 empty] | PHASE ONE | [44 empty] | PHASE TWO | [44 empty] | PHASE THREE | [44 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 0 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18 |  |  |  |  | WEEK 19 |  |  |  |  | WEEK 20 |  |  |  |  | WEEK 21 |  |  |  |  | WEEK 22 |  |  |  |  | WEEK 23 |  |  |  |  | WEEK 24 |  |  |  |  | WEEK 25 |  |  |  |  | WEEK 26 |  |  |  |  | WEEK 27 |  |  |  |  | WEEK 28 |  |  |  |  | WEEK 29 |  |  |  |  | WEEK 30 |  |  |  |  | WEEK 31 |  |  |  |  | WEEK 32 |  |  |  |  | WEEK 33 |  |  |  |  | WEEK 34 |  |  |  |  | WEEK 35
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
Level 1 | Project ideas and planning | bar: WEEK 16 M to WEEK 35 F
1.1 | App ideas | Project management team | 2021-08-25 | 2021-09-03 | 9 | 100%
| Research | Project management team | 2021-09-01 | 2021-09-06 | 5 | 100%
| Projections | Project management team | 2021-09-08 | 2021-09-14 | 6 | 100%
| Stakeholders | Project management team | 2021-09-08 | 2021-09-14 | 6 | 100%
| Schedules | Project management team | 2021-09-13 | 2021-09-16 | 3 | 100%
| Project initiation | Project management team | 2021-09-08 | 2022-01-26 | 140 | 90%
Level 2 | Project requirements and interfaces | bar: WEEK 16 M to WEEK 35 F
| HL analysis | Data analyst | 2022-01-03 | 2022-01-17 | 14 | 0% | bar: WEEK 0 M to WEEK 2 Th
| DL core analysis | Data analyst | 2022-01-18 | 2022-02-25 | 38 | 0% | bar: WEEK 3 M to WEEK 10 W
| DL support analysis | Data analyst | 2022-02-16 | 2022-03-28 | 40 | 0% | bar: WEEK 2 Th to WEEK 10 W
| Infrastructure | UX / UI designer | 2022-01-18 | 2022-02-07 | 20 | 80% | bar: WEEK 3 M to WEEK 6 F
| GUI | Digital designer / Frontend developers | 2022-02-16 | 2022-03-17 | 29 | 100% | bar: WEEK 2 Th to WEEK 8 T
| Junior interface | Digital designer / Frontend developers | 2022-03-10 | 2022-03-21 | 11 | 0% | bar: WEEK 1 W to WEEK 3 W
| Senior interface | Digital designer / Frontend developers | 2022-03-20 | 2022-04-07 | 18 | 0% | bar: WEEK 3 W to WEEK 6 F
Level 3 | Project User/App systems | bar: WEEK 16 M to WEEK 35 F
| Payment system | Backend developers | 2022-03-20 | 2022-03-25 | 5 | 0% | bar: WEEK 3 W to WEEK 4 T
| Application system | Backend developers | 2022-03-20 | 2022-04-19 | 30 | 0% | bar: WEEK 3 W to WEEK 7 T
| Support system | Backend developers | 2022-05-04 | 2022-05-13 | 9 | 0% | bar: WEEK 18 T to WEEK 19 F
| User system | Backend developers | 2022-04-08 | 2022-05-10 | 32 | 0% | bar: WEEK 12 Th to WEEK 18 F
| Database | Backend developers | 2022-02-16 | 2022-04-06 | 49 | 0% | bar: WEEK 2 Th to WEEK 12 T
Level 4 | Project Performance/Monitoring | bar: WEEK 16 M to WEEK 35 F
| 360 testing | QA Engineer | 2022-05-19 | 2022-06-13 | 25 | 0% | bar: WEEK 21 M to WEEK 25 F
| Documentation | Document Review Analyst | 2022-06-13 | 2022-07-21 | 38 | 0% | bar: WEEK 25 F to WEEK 33 T
| Agile testing | QA Engineer | 2022-01-03 | 2022-06-12 | 160 | 0% | bar: WEEK 0 F; WEEK 1 F; WEEK 2 F; WEEK 3 F; WEEK 4 F; WEEK 5 F; WEEK 6 F; WEEK 7 F; WEEK 8 F; WEEK 9 F; WEEK 10 F; WEEK 11 F; WEEK 12 F; WEEK 13 F; WEEK 14 F; WEEK 15 F; WEEK 16 F; WEEK 17 F; WEEK 18 F; WEEK 19 F; WEEK 20 F
CLICK HERE TO CREATE WBS OUTLINE AND DIAGRAM TEMPLATES IN SMARTSHEET | bar: WEEK 0 M to WEEK 11 F