## Ark1
WBS2 | WBS3 | Work package | O | /ML | /P | Resources (% in project/work package) | PERT effiecient work hours | (calendar hours) | calendar days | calendar weeks | Calendar PERT duration workhours | /work days | /work weeks | PERT resource estimation |  |  | CPM activity |  | Activity detail | Earliest start | Length in calender days | Dependant on CPM activities | Type | Critical Path | Node / Network point
Junior Interface | Application | Job interview | 8 | 12 | 18 | 1 UI/UX designer 1 SW WebDev, BackendDev (Fullstack) | 12 | 15 | 1.875 | 0.375 |  |  |  | Efficiency | 75% | 1.25 | A | HL Analysis | High level analysis infrastructure/core/support | 1 | 12.5 | none |  | Yes
Junior Interface | Application | CV | 6 | 10 | 16 |  | 10 | 12.5 | 1.5625 | 0.3125 |  |  |  | Paid hours | 8 |  | B | Infrastructure | Select, install, configure | 3.5 | 10 | none | Sequential | Yes | 1-2 /A
Junior Interface | Application | CPR Training | 8 | 12 | 18 |  | 12 | 15 | 1.875 | 0.375 |  |  |  | Efficient hours | 6 |  | C | DL Analysis core | Core requirements/interdependencies/GUI | 5.5 | 18.75 | A |  | Yes
Junior Interface | Application | [5 empty] | 34 | 42.5 | 5.3125 | 1.0625 | 42.5 | 5.3125 | 1.0625 | Days in a week | 5 |  | D | DL Analysis support | Core requirements/interdependencies/GUI | 9.25 | 18.75 | D |  | No
[17 empty] | E | GUI | Design, functionalities, menu, login | 13 | 5.9375 | B |  | Yes | 4-5 /C
Junior Interface | Booking system | Job application | 10 | 14 | 20 |  | 14 | 17.5 | 2.1875 | 0.4375 | [6 empty] | F | Junior interface | Design, functionalities, application | 14.1875 | 5.9375 | B, C |  | Yes | 7-8/D
Junior Interface | Booking system | Call notification | 8 | 7 | 7 |  | 7 | 8.75 | 1.0938 | 0.21875 | [6 empty] | G | Senior interface | Design, functionalities, services | 15.8438 | 8.2812 | B, C |  | No | 4-5 /E
Junior Interface | Booking system | [5 empty] | 21 | 26.25 | 3.2812 | 0.65625 | 26.25 | 3.2812 | 0.65625 |  |  |  | H | Application | Requirements, Interviews, Jobs list | 18.3438 | 12.5 | A, D |  | Yes | 6-7 /F
[17 empty] | I | Support system | Tutorials/DM/Contact number | 19.4062 | 5.3125 | A, B, C, D, E |  | No | 7-8 /
Junior Interface | Profile page | Description | 8 | 8 | 12 |  | 8 | 10 | 1.25 | 0.25 | [6 empty] | J | User system | User login/register | 21.4062 | 10 | F, G, H, I |  | Yes
Junior Interface | Profile page | Video presentation | 8 | 10 | 21 |  | 10 | 12.5 | 1.5625 | 0.3125 | [6 empty] | K | Documentation | Infrastructure/Core/Support | 21.4062 | 20 | B, C, D, E |  | Yes
Junior Interface | Profile page | Reviews | 8 | 20 | 25 |  | 20 | 25 | 3.125 | 0.625 | [6 empty] | L | Database | Setup and design the database that stores information | 26.4062 | 25 | C, D, E, F |  | No | 3-5 /I
Junior Interface | Profile page | Notifications | 8 | 15 | 22 |  | 15 | 18.75 | 2.3438 | 0.46875 | [6 empty] | M | Payment system | Secured, intuitive and fast system | 27.4062 | 5 | A, B, C |  | No | 6-7 /
Junior Interface | Profile page | [5 empty] | 53 | 66.25 | 8.2812 | 1.6562 | 66.25 | 8.2812 | 1.6562 |  |  |  | N | 360 Testing | All modules testing |  | 2.5 | A, B, C, D, E, F, G, H, I, J |  | No | 1-8 /
O
Senior Interface | Booking system | Category list | 8 | 16 | 24 |  | 16 | 20 | 2.5 | 0.5 | 20 | 2.5 | 0.5
Senior Interface | Booking system | Job request | 8 | 16 | 24 |  | 16 | 20 | 2.5 | 0.5 | 20 | 2.5 | 0.5
Senior Interface | Payment system |  | 8 | 16 | 24 |  | 16 | 20 | 2.5 | 0.5 | 20 | 2.5 | 0.5 |  |  |  |  | 3 | 2 | 5
[18 empty] | B | Infrastructure
[18 empty] | 4.75 | 1.75 | 6.75 |  |  | 7.75 | 3 | 10.75 | 11.75 | 1.1875 | 12.9375 | 13.9375 | 1.6562 | 15.5938
Senior Interface | Profile page | Description | 4 | 8 | 16 |  | 8 | 10 | 1.25 | 0.25 | [12 empty] | F | GUI |  | G | Junior interface |  | H | Senior interface
Senior Interface | Profile page | Reviews | 4 | 8 | 16 |  | 8 | 10 | 1.25 | 0.25 | [12 empty] | 11 | 3.25 | 14 | 15 | 3.25 | 16.1875 | 17 | 3.0625 | 18.6562
Senior Interface | Profile page | Notifications | 8 | 16 | 24 |  | 16 | 20 | 2.5 | 0.5
Senior Interface | Profile page | [5 empty] | 32 | 40 | 5 | 1 | 40 | 5 | 1
[14 empty] | 1 | 2 | 2 |  | 3 | 3.75 | 6.75 | [11 empty] | 20.25 | 0.5 | 20.75 | 21.75 | 2 | 23.75 | 24.75 | 4 | 28.75
General interface | Login | Registration form | 8 | 10 | 14 |  | 10 | 12.5 | 1.5625 | 0.3125 |  |  |  | A | HL Analysis |  |  | C | DL Analysis core | [12 empty] | I | Support system |  | N | 360 Testing |  | K | Documentation
General interface | Graphics | Graphics | 8 | 13 | 18 |  | 13 | 16.25 | 2.0312 | 0.40625 |  |  |  | 1 | 0 | 2 |  | 3 | 0 | 6.75 | [11 empty] | 20.25 | 0 | 20.75 | 21.75 | 0 | 23.75 | 24.75 | 0 | 28.75
General interface | Accessibility | Navigation | 10 | 15 | 21 |  | 15 | 18.75 | 2.3438 | 0.46875
General interface | [6 empty] | 38 | 47.5 | 5.9375 | 1.1875 | 47.5 | 5.9375 | 1.1875
Infrastructure | Software | Database | 12 | 18 | 24 |  | 18 | 22.5 | 2.8125 | 0.5625
Infrastructure | Software | Security | 14 | 20 | 26 |  | 20 | 25 | 3.125 | 0.625 | [12 empty] | 7.75 | 5 | 12.75 | 13.75 | 2.5 | 16.25 | 17.25 | 2 | 19.25
Infrastructure | Software | Basic software | 2 | 4 | 6 |  | 4 | 5 | 0.625 | 0.125 | [12 empty] | M | Database |  | I | Application |  | K | User system
Infrastructure | Hardware | Servers | 12 | 18 | 24 |  | 18 | 22.5 | 2.8125 | 0.5625 | [12 empty] | 8 | 0.25 | 13 | 14 | 0.25 | 16.5 | 17 | -0.25 | 19
Infrastructure | Hardware | Phone | 2 | 4 | 6 |  | 4 | 5 | 0.625 | 0.125
Infrastructure | [6 empty] | 64 | 80 | 10 | 2 | 80 | 10 | 2
Analysis | HL Analasys |  | 70 | 80 | 90 |  | 80 | 100 | 12.5 | 2.5 | 100 | 12.5 | 2.5
Analysis | DL Analysis core |  | 90 | 120 | 200 |  | 120 | 150 | 18.75 | 3.75 | 150 | 18.75 | 3.75 | [12 empty] | 13.75 | 1 | 14.75
[26 empty] | N | Payment system
Analysis | DL Analysis support |  | 85 | 120 | 250 |  | 120 | 150 | 18.75 | 3.75 | 150 | 18.75 | 3.75 | [12 empty] | 18 | 4.25 | 19
GUI
[23 empty] | 7.75 | 3.75 | 11.5
Testing | Agile testing | [21 empty] | D | DL Analysis support
Testing | 360 testing | [21 empty] | 17 | 9.25 | 20.75
Testing
Total worktime |  |  | 180 | 290 | 406 |  | 532 | 665 | 83.125 | 16.625 | 362.5 | 45.3125 | 9.0625